## Task Status & Deadline
Task | Status | Assigned | Deadline | Notes/Comments | Estimated Hours | Estimated Hours = timeUnderstand + timeCode + timeTest
Bot Foundation/Infrastructure: programming templates for easy, medium, hard | Completed | Marie | 2026-10-04 |  | 3 | timeU = 0.5 timeC = 2 timeT = 0.5
How to Make a Bot/Reinforcement Learning: code template/comments | Completed | Jaydine | 2026-10-04 |  | 2.5 | timeU = 0.5 timeC = 1.5 timeT = 0.5
UI Fixes: ensuring interface.py & main.py work on windows/mac | Completed | Lauren | 2026-10-06 |  | 1.5 | timeU = 0.25 timeC = .75 timeT = 0.5
Bot UI Components, integrate with Interactive and Auto Modes | Completed | Marie | 2026-10-06 |  | 2 | timeU = 0.5 timeC = 1 timeT = 0.5
Easy Solver | Completed | Kaitlyn (support from Jaydine) | 2026-10-08 |  | 1.25 | timeU = 0.25 timeC = 0.75 timeT = 0.25
Medium Solver | Completed | Greeshma | 2026-10-08 |  | 3 | timeU = 1 timeC = 1.5 timeT = 0.5
Hard Solver | Completed | Jaydine | 2026-10-08 |  | 2.75 | timeU = 0.5 timeC = 1.75 timeT = 0.5
Custom Enhancements: likely timer with high score? | Completed | Ximena | 2026-10-08 |  | 2.25 | timeU = 0.5 timeC = 1.25 timeT = 0.5
System Documentation: documenting previous team's code, adding comments, estimated hours methodology, actual hours, etc | In Progress | Marie | 2026-10-11 |  | 3 | timeU = 0.5 timeC = 1.5 timeT = 1
GitHub Management | Completed | Kaitlyn | 2026-10-11 |  | N/A
Testing/Integration | Completed | All members | 2026-10-10 | Making sure integrates across OSs | 2 | timeU = 0.5 timeC = 1 timeT = 0.5
System Diagrams: Data flow diagram + Custom Enhancement Diagram | Not Started | Sabelli | 2026-10-10 | Process Diagram | 1.5 | timeU = 0.25 timeC = 1 timeT = 0.25

## Greeshmas Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04
2026-10-05
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11

## Jaydines Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04
2026-10-05 | Bot Solver Templates | 1 | Created templates for teammates to use for easy, medium, and hard solvers
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
2026-10-07
2026-10-08 | Hard Solver | 2 | Implement and test the hard solver.
2026-10-09 | Bug Fixing | 3 | Find and fix bugs
2026-10-10
2026-10-11 | System documentation/final code cleanup | 2 | System architecture diagram/hour tracking and removing any remaining TODO or FIXME comments in the code

## Kaitlyns Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-28 | Fork Repo and set up ruleset | 1 | Took a little while to get the ruleset to work correctly
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04 | Updated Git guide document | 2 | Did research and updated Git guide with commands for working on a forked repo, checking branches, and keeping them up to date with main.
2026-10-05 | Implemented easy_solver.py | 1 | Finished code for easy_solver
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
2026-10-07 | Research on how to check for merge conflicts on branches several commits behind main | 1.5 | Learned how to test merge team members' branches into main to check for conflicts without committing the merge. Used git commands to verify pull requests could be merged safely.
2026-10-08
2026-10-09 | updated easy_solver.py | 0.5 | Added comments
2026-10-10
2026-10-11 | Clean up unnecessary files and remove all branches besides main on Github | 0.5

## Laurens Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04
2026-10-05 | UI Bug Fixed | 1 | revealed cells do not changes color. assuming blank image covering up the cell, though it creates more problems
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
2026-10-07 | Completed | 1 | revealed cells identified as 0 and macbook users also can flag with control+mouseclick
2026-10-08
2026-10-09
2026-10-10
2026-10-11

## Maries Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04 | Adding comments to old team's code, AI Solver templates, setup_menu template, custom feature template | 3
2026-10-05
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
| System Documentation (estimated hours, architecture) | 2
2026-10-07
2026-10-08 | Bot UI Components + Interactive and Auto Solver integration | 1.5
2026-10-09 | Bug Fixing | 3 | Find and fix bugs
2026-10-10 | System Documentation | 2 | Finishing touches
2026-10-11

## Sabellis Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11

## Ximenas Hours
Day | Task | Hours Worked | Notes/Comments
2026-09-29 | Team Meeting w/ TA | 1 | Project Kickoff meeting
2026-09-30
2026-10-01
2026-10-02
2026-10-03 | Virtual Meeting w/ Team | 1 | Project Planning/Allocating Tasks
2026-10-04
2026-10-05
2026-10-06 | Team Meeting w/ TA | 1 | Project Status Updates
2026-10-07 | Custom Addition | 6 | Completed timer.py, Updated interface.py and main.py
2026-10-08
2026-10-09
2026-10-10
2026-10-11